## Sheet1
web link
https://demo.akaratmisr.com/en/account/login
admin link
https://akaratmisr.com/en/admin/auth
user haiderali11 password 12345thn
apis link
https://demo.akaratmisr.com/docs/#!/auth/icodedesigns_0
tasker add property images not work
representative add property images not work and photoid not working

## issues
S.no | Bugs point | Bug | Status | Case
1 | facebook login api | erron on log in | PENDING | NABEEL
2 | facbook register | Trying to register by facebook, then this happens | PENDING | NABEEL
3 | google register | no register in apk (GOOGLE DEVELOPER ACCOUNT) akaratmisr.com@gmail.com akaratmisr11321 | PENDING | NABEEL
4 | profiles pages(tasker) | i can work render should be format data send should be key | FIX | ABDULLAH
5 | profiles pages | state render should be format data send should be key(now format sending to data base) | PENDING | NABEEL
6 | profiles pages | url no render on fields | FIX | ABDULLAH
7 | profiles pages(tasker) | home tel fax and company name check also skype twitter google pus linkdin | FIX | ABDULLAH
8 | profiles pages(Representative) | Representative profile screen on the web, please see "You can cover areas" then comprare on the web | PENDING | NABEEL
9 | my payment | When i click on upgrade package from here, seem like it's no auto login to billing.akaratmisr.com. could you please use the same link when click on upgrade package on profile page to open webview here | FIX | NABEEL
10 | profiles pages | after update pack should be real time | PENDING | NABEEL
ABDULLAH
11 | on edit property | On edit properties, it shows 2 selected but when i click on the list, i can't see these categories | PENDING | ABDULLAH | wrong data type from api
12 | add project (Representative acc) | See that, the same representative user, but can't choose district, subdistric | PENDING | ABDULLAH
13 | add project (Representative acc) | The same rep account, please remove " type" on mobile, i don't see this on the web | PENDING | ABDULLAH
14 | add project (Representative acc) | Please use the api below for this category({domain}/{language}/api/dataselect/getNewCategoryProperty) | PENDING | ABDULLAH
15 | add project (Representative acc) | This is on mobile, can only add gallery (feature photo not available) | PENDING | ABDULLAH
16 | add project (Representative acc) | After i add new property from here, it's not back to this screen to continue to add new project. By the way, "assign from current property" have you guys do any action on this? The property that added from here seem like not working right, each time i submit, it required a field but i remember i filled in all field | PENDING | ABDULLAH
|  |  | PENDING | ABDULLAH
|  |  | PENDING | ABDULLAH
17 | signup on tasker | On screen register representativev, please uncheck " i will provide it later" because documents are required here | FIX | ABDULLAH
18 | signup on international partner | Please also uncheck this on register international partners too coz documents are required | FIX | ABDULLAH
18 | add property | on add and edit property, please remember that always post "contact_price" to server. There maybe something wrong on edit property because after a property is added successfull, I chose to edit screen of that one and click submit without any change, but an aleart is showed to required field | PENDING | ABDULLAH
|  |  | PENDING | ABDULLAH
19 | GOOGLE MAP | GOOGLE MAP NOT WORKING BECAUSE KEY NOT AVAILABLE | PENDING | ABDULLAH

## Sheet3
ANDROID_HOME | C:\Users\Dot n dot graphics\AppData\Local\Android\Sdk
JAVA_HOME | C:\Program Files\Java\jdk1.8.0_201
Path | C:\Users\Dot n dot graphics\AppData\Local\Programs\Microsoft VS Code\bin
C:\Users\Dot n dot graphics\AppData\Local\Yarn\bin
C:\Users\Dot n dot graphics\AppData\Local\Android\Sdk\platform-tools
C:\Users\Dot n dot graphics\AppData\Local\Android\Sdk\tools
C:\Users\Dot n dot graphics\AppData\Local\Android\Sdk\tools\bin
C:\Users\Dot n dot graphics\AppData\Local\Android\Sdk\emulator
%USERPROFILE%\AppData\Local\Microsoft\WindowsApps
C:\Users\Dot n dot graphics\AppData\Roaming\npm
edit ok buyer req